## General
Audit Recommendations Monitor
2025-07-31
Report / Action | Recommendation | Action Owner | Grade | Original timescale | Status at July 2025 | Expected Completion Date | South Lanarkshire College management update as at 31 July 2025 | Evidence Supplied
2021/22
Cyber Security 2022-03 R7 | The Incident Response Process, and supporting playbooks, should be tested by way of a scenario-based desktop exercise to ensure staff know how to respond during an incident, and to also highlight any problem areas in the planned response. | Heads of IT and HR and the Clerk to the Board | 2 | 2023-03-31 | Fully implemented | 2025-09-30 | Incident response documents exist along with playbooks. Will need review and updated. Update - Due to the changes in SLT staff following the restructure, it makes sense to move this back to later in the year or next session. Realistically it could be Sept 2025 before completion.
Health & Safety | We recommend the reporting of an Annual Health and Safety Report be incorporated into the forward workplan for the Human Resources Committee to ensure that Board Members have the opportunity to consider and approve the annual report and the forward workplan for health and safety activity for the coming year. | Head of Facilities & HS | 3 | 2022-12-31 | Partially complete | 2025-11-30 | An annual report will be produced reporting on what has been completed during the year and set out the priorities and targets for the coming year. Staff absence has caused a delay in this piece of work progressing more fully but it will be carried out imminently for review at a future HR Committtee.(CF) Aug '25 - Date moved out to allow for completion of report
2022/23
Staff Recruitment & Retention 2023-03 R1 | It is recommended that the College define timeframes for completion of the ongoing review of its recruitment and selection policies to ensure that these are completed in a timely manner and are issued to the relevant staff for their understanding. | Head of HR | 2 | 2024-01-20 | Partially implemented | 2025-12-01 | Due to capacity issues within the HR team, the development of the policy has been delayed. The Policy is now in draft form and is currently going through an internal HR review before moving to the Senior Leadership Team, the Joint Negotiation Committee, the HR Committee and then the Board of Management.
Staff Recruitment & Retention 2023-03 R2 | It is recommended that the College prepare procedural documents to formally document the administration processes to be followed when recruiting a new member of staff, to ensure that the process can be consistently performed by anyone in the event of staff absences / unexpected turnover. | Head of HR | 3 | 2024-05-20 | Partially implemented | 2025-12-22 | There has been delays with the role out of iTrent features, including the Recruitment module. The priority has been in ensuring payroll and pensions accuracy. Employee Self-Service has now been rolled out, and the College is seeking to implement the recruitment module during the first half of the next academic year. In saying that, the module is already well developed and partially tested.
Staff Recruitment & Retention 2023-03 R5 | It is recommended that the College set out a clear timeline for importing all relevant hard copy documentation to the new HR system iTrent, to ensure that this data transfer is completed in a timely manner and to avoid a protracted scenario where some information is held electronically and some information is still held in hardcopy files | Head of HR | 3 | 2024-05-20 | Little or no Progress | 2026-03-31 | The new HR & Payroll system is not fully in place yet. It is envisaged that a subsequent project to upload hard-copy documentation will follow this and will likely commence around December 2025
Budgetary Control 2023-04 R1 | The College should develop a formal budget setting timetable, setting out all key activities in the budget setting process from end to end, to ensure that all activities are completed timeously. The timetable may also assign tasks to responsible individuals, with target completion dates aligned with the Finance and Resources Committee meeting as appropriate. | VP - Finance, Resources & Sustainability | 3 | 2024-01-31 | Partially implemented | 2025-10-31 | August 2024 - This is still in progress. Budget Preparation guidance document prepared, which builds out the intended timeline for budget setting in accordance with the wider curriculum planning exercise. Update - Alongside the Budget Prep guide, Finance are developing a GANTT chart to formalise the timetable.
Budgetary Control 2023-04 R2 | The College should consider developing enhanced real time financial information and dashboards, perhaps via Power BI, to allow Budget Holders to monitor actual income and expenditure against budget in real time. | VP - Finance, Resources & Sustainability | 3 | 2024-02-29 | Partially implemented | 2025-10-31 | August 2024 - The College currently utilises Power BI for many reporting purposes within finance - one example is the temporary lecturing budgets. Further enhancements are required to ensure quality of data entry. The MIS developer team have also worked with Finance during the year to develop a schedule of reportable monthly income to enable income accruals to be booked for month end reporting purposes. This needs to be further developed to improve accuracy and to ensure it captures all income sources Update - Work undertaken to develop a monthly management account pack, which will give enhanced information to budget holders. This will include area specific actual vs budget data, with two-way commentary
Budgetary Control 2023-04 R3 | The Finance team should document the month end process currently followed by Finance, including preparation of budgeting information to allow for prompt publication of income and expenditure by budget line for review and monitoring by Budget Holders. This should be adapted as the capabilities of BluQube are enhanced to include generation of reports immediately following the completion of the month end close process to provide timely information. | VP - Finance, Resources & Sustainability | 3 | 2024-03-31 | Partially implemented | Dec-25 | August 2024 - The capabilities of Bluqube are now being discussed. A kick off meeting with Bluqube has been initiated for Thursday 29th August, with a consultant coming on site to enable changes on Sept 3rd. The College has now purchased the reporting package that bolts onto Bluqube and this will enable purpose built reports to be run once structures are set up. Update - Finance use a checklist to complete the monthly management accounts. There are plans to replace the current management account pack to enhance the process. There are also plans to enhance BluQube to include budget information, to allow for a better user experience.
Budgetary Control 2023-04 R4 | The College should develop a formal training programme for Budget Holders, which they are required to complete before they undertake their budget monitoring role. Detailed written procedures and guidance documents should also be developed (in parallel with the development of this tailored training for Budget Holders). This will provide a useful reference document for all Budget Holders, which they can consult, as required, following the training. | VP - Finance, Resources & Sustainability | 3 | 2024-05-31 | Little or no Progress | Mar-26 | April 25 - A formal training programme has yet to be put in place but allowing for 6 month period to embed the Bluqube reporting package and have it fully operational, the College would expect to roll out training to budget holders in conjunction with new reporting system capabilities in 25/26. Update - Progress had been hampered by the restructure, following VS process. The relevant users have now all been identified, so work can begin to train them. Budget process set for 2025/26, so focus will be on the next financial year.
Student Support Funds 2024-08 R1 | The College should ensure that distribution lists identifying Bursary students in receipt of study materials are maintained for each purchase invoice charged to the Bursary fund. Based on the current approach, the College should ensure that the planned study costs for each course still reflect the specific items or materials needed for the course and the current price from suppliers. | Management Accountant | 3 | 2024-02-29 | Little or no Progress | 2026-02-28 | The College will continue to analyse all study costs monthly and reconcile them back to Cost of Course forms, adjusting the Teqios system where required, and reconciling this to the general ledger. With regards to distribution lists, the College has implemented a document during the monthly reconciliation process that lists all bursary students and their course code/spend available however this did not tie in to actual spend. The College therefore accepts the action required now to attach actual spend to this document and will work with the curriculum managers to see if a better record of study cost spend can be kept at class level. The College commits to resolving this over the summer with a view to it being evidenced and confirmed in the next FES return audit in Sep 25. Update - Initiated the set-up of study kit lists in similar format to those used by Hairdressing dept for each dept.
Student Support Funds 2024-08 R4 | Ensure that a check is made on the categorisation of ASN costs to ensure that they are correctly disclosed on the FES return. | Management Accountant | 3 | 2024-02-29 | Little or no Progress | 2026-02-28 | The monthly categorisation check of FES categories will include a check of ASN costs to ensure that they are being disclosed correctly going forward. This is monitored from Aug - Jan then implemented from Feb - Jun once full quote of students are included on the FES return. Update - Unable to receive a monthly FES to check due to time constraints of other departments. Work to be done between MIS and Finance to ensure ability to check the data.
2023/24
Publicity & Communications | Crisis communication training should be delivered for the Principalship and the Marketing and Communications Manager. | VIce Princioal - Learning, Teaching & Student Experience | 3 | 2024-07-31 | In progress | Mar-26 | The Principal and Vice-Principal for Learning, Teaching & the Student Experience are comfortable with the level of training they have received to date. The Vice Principal - Finance, Resources & Sustainability and the Marketing and Communications Manager will undertake Media/Crisis Training with Police Scotland. Due to illness, the Vice Principal was unable to attend the event on 25th March 2025. Another session will need to be booked in its place.
Procurement & Creditors/Purchasing 2024-03 R1 | It is recommended that consideration be given to amending the approvals of low value purchase orders in PECOS to Vice Principals and Associate Principals (rather than requiring sign off by the Principal), to reduce the risk of a bottleneck. | Vice Principal - FInance, Resources & Sustainability | 3 | 2024-06-30 | Partially implemented | Oct-25 | Given the ongoing College restructure and work that will be required to change the system parameters for new authorisations, this task has been delayed until a new College structure has been finalised to avoid unnecessary rework. Update - Progress made. Procurement thresholds to be taken to board for approval, and implementation will occur thereafter
Student Activity (Credits) 2024-07 R1 | Allocation of Credits to Courses For all College devised units, the College should ensure that adequate supporting evidence is available for planned learning hours to verify the Credits claim. | Head of MIS (Chris Sumner) | 3 | Sep-25 | Partially implemented | Sep-25 | College Units or “Non-SQA” units are a frequent issue. While I agree with the recommendation to get better at reporting the evidence, the college uses far fewer non-SQA units in their courses than previous years. That said, the timetabling and attendance for these modules needs improved using our current timetabling system. We will monitor this more closely with he timetabled hours vs actual hours power reporting as this was invaluable in the audit. At curriculum planning process, the CM’s will be challenged for using the non-SQA units, preventing unnecessary use of units in the courses. Record of work evidence is a lot clearer this year and can be used as supportive evidence for these modules.
Student Activity (Credits) 2024-07 R2 | Required Dates and Attendance Ensure that the required dates for programmes and students recorded on the FES1 and FES2, respectively, are calculated in line with the Credits guidance. | Head of MIS (Chris Sumner) | 3 | Sep-25 | Partially implemented | Sep-25 | Required date issues was not an issue at course level but it was at student level if the student finished early. The power bi report we use for checking the required date has been modified so we can see the student required date might be incorrect and reviewed at each FES quarter returns. The report was updated and being reviewed by the staff. However, there is a question around the validity of moving a required date that we need to speak to the auditors about as it changes the way SFC view the required date. (CS to follow up with HL)
Student Support Funds 2024-08 R2 | The College should ensure that expenditure is correctly categorised on the study costs spreadsheet to allow a more accurate comparison of planned and actual expenditure. | Management Accountant | 3 | Dec 24 | Little or no Progress | 2026-02-28 | The cost of course forms will be updated to show a more realistic split of bursary spend for each department, departments that have ‘other’ as a category of spend with no history of any actual spend within this category will have this amount spread over the other categories based on likely spend. Invoices that have a number of different categories of bursary spend will be allocated accordingly. Update - This work will tie in with the development of the study kit lists to get a better idea of what each course will likely spend on each category. Cost of course forms will be tailored to match the study kit lists.
Student Support Funds 2024-08 R3 | The College should review student Award Assessment categorisation on the FES and ensure that any apparent misstatements are fully investigated and resolved | Management Accountant | 3 | Dec 24 | Little or no Progress | 2026-02-28 | The monthly categorisation check of FES categories will include a check of ASN costs to ensure that they are being disclosed correctly going forward. This is monitored from Aug - Jan then implemented from Feb - Jun once full quote of students are included on the FES return. Update - Unable to receive a monthly FES to check due to time constraints of other departments. Work to be done between MIS and Finance to ensure ability to check the data.
Businss Process Review Space Management/Room Utilisation | The College's Estate Strategy needs to be updated to reflect the current space requirements of the curriculum, staff, and students. | Head of Estates | N/A | 2024-11-30 | In progress | Dec-25 | The existing Estates Strategy is very outdated but an update has started and will be progressed in the coming months. Aug '25 - Date extended out to allow time to carry out
Businss Process Review Space Management/Room Utilisation | A centralised room booking system is required that is visible by the whole College. | Head of MIS/Head of Estates | N/A | 2025-08-31 | Not yet started | Dec-25 | The College agrees that there needs to be timetabling protocols and a room booking system that is visible and can be used by the whole College. This then allows for room utilisation data to be monitored. Apr '25 - New access control system and future tech to assist in enabling this. Date extended due to delay in tendering process CF
Businss Process Review Space Management/Room Utilisation | Space management objectives and room utilisation targets need to be clearly defined in policies and procedures, accompanied by a structured space utilisation monitoring process. | Head of Curriculum/Head of Estates/Head of MIS and Vixe Principal - Finance | N/A | 2025-12-23 | Not yet started | Dec-25 | Management agrees that policies and procedures (timetabling protocols and room booking) should be developed for cross college use. This is to be led by the curriculum area to enable support function departments to have systems in place. Apr '25 - Once procedures are in place, room utilisation can also use future access control technology for streamlined process CF
2024/25
Payroll and Pensions Management | Review the capability within its Payroll team to prepare and submit the SPF member data for College employees in a timely and accurate manner. The College should consider strengthening the review and approval controls in place in relation to the data being submitted to the pension scheme administrators to minimise the risk of errors and subsequent inefficiencies in resolving SPFO’s and employees’ queries. The College should ensure that it is actively monitoring and enforcing the submission of accurate member data to ensure that the scenario where member data is out of date by several months does not reoccur. | Head of HR | N/A | 45808 | Complete | May-25 | Completed
Payroll and Pensions Management | The College should ensure that multiple employees, across both Payroll and HR departments, have access to e-mail inboxes where queries can be received from pension scheme members in relation to the College’s management of their pension data. This is especially important due to the high risk of errors and misalignment between data held by the College and the pension scheme administrators, as demonstrated throughout our review. | Head of HR | N/A | 2025-08-31 | Complete | 2025-07-01 | Completed
Payroll and Pensions Management | The College should conduct a post-implementation review to provide confirmation that the new Payroll / HR system – iTrent – is configured in a way that provides adequate functionality for the management of employee pension data and allows the accurate, timely and efficient submission of required information to the pension scheme administrators. | Head of HR | N/A | 2025-05-31 | In progress | Dec 25 | This is in progress
Payroll and Pensions Management | The College should ensure that the new Payroll / HR system – iTrent – is configured in a way that offers adequate functionalities for managing employee pension data and assisting in accurately and efficiently submitting it to the pension scheme administrators. | Head of HR | N/A | 2025-05-31 | In progress | Dec-25 | This is in progress; additional modules to be rolled out to enhance these functionalities
Payroll and Pensions Management | Pension scheme members’ leaving status should be communicated to the relevant pension agency promptly, accurately, and in line with their requirements. The College should review its controls around managing employee data on its payroll system and ensure that any staff members are removed from it on their actual leaving date. It should be made impossible to pay staff members who have left the College through regular payroll payment runs. Monitoring controls should be introduced (potentially independent to the Payroll team) over the payroll payment runs to ensure that no ex-employees are included in payroll payment runs past the month in which they have left the organisation. | Head of HR | N/A | 2025-04-30 | In progress | Dec-25 | Complete, with the exception of the reports being used as monitoring controls, which commence in April 2025 and likely be in place for Dec 2025 owing to ongoing work to devise appropriate monitoring reports in iTrent.
Payroll and Pensions Management | The College should ensure that adequate internal controls are in place to prevent and detect illegitimate payroll transactions, ex-employees being included within payroll processing, and errors. Risk-averse monitoring, review, and approval controls should be implemented (or strengthened) to ensure sufficient segregation of duties in processing the payroll. The capabilities of the new iTrent HR & payroll system should be leveraged to establish appropriate user access rights and embed approval controls within the process. | Head of HR | N/A | 2025-04-30 | In progress | 2025-12-01 | Complete; certain illegitimate processes are impossible in the new system and approvals are in place for most aspect, Can be more widely demonstrated as further modules are rolled out..
Payroll and Pensions Management | The College should consider undertaking a detailed exercise to determine how the historical overpayments to employees and pension schemes, as well as underpayments to HMRC, should be addressed and communicated to staff and other relevant stakeholders, including HMRC. The College should consider whether it has a complete view of instances where the ‘salary advance’ or other illegitimate adjustments were utilised and should take steps to determine whether these adjustments to HMRC payments are in any way connected to the fines levied by HMRC against the College in recent years | Head of HR | N/A | 2025-07-31 | In progress | 2025-12-01 | This is in progress
Payroll 2025-02 | The College should establish aprocedure for processing changes to employee standing data. This procedure should introduce a requirement that the staff member receiving and processing the request should independently confirm the request as genuine via a direct conversation with the relevant employee, for example by making a phone call and asking the employee to verify their new bank details (if the change relates to bank details). This should be carried out whether the request was received from a College email account or a non-College email account. A note to confirm that the change hasbeen verified directly with the relevant employee should be retained on file. Payroll Administrators, who are processing any requests for changes to employee standing data, should ensure that the source of the request to change employee data (such as a letter or email) is filed down appropriately, in order to provide an audit trail. | Head of HR | 3 | 2025-05-31 | Complete | 2025-05-31 | Update- The College agreed the recommendation and put in place procedures for processing changes to employee standing data immediately.