## General
Audit Recommendations Monitor
19th August 2024
Report / Action | Recommendation | Action Owner | Grade | Original timescale | South Lanarkshire College management update as at April 2020 | Status at 19 August 2024 | Expected Completion Date | South Lanarkshire College management update as at 19th August 2024 | Evidence Supplied
2021/22
Cyber Security | Mechanisms should be established for testing the effectiveness and value for money of the security training provided to staff. The areas of the organisation that regularly feature in security reports, or achieve the lowest feedback from information security questionnaires, should be targeted for further tailored training activity. | Head of IT and Clerk to the Board | 3 | 2023-06-30 |  | In progress | 2024-09-01 | We are currently working with JISC on such topics of the pen testing and phishing scam testing to test effectiveness. Unfortunately, we need to wait until training has been completed to fully assess the staff. This is due to be completed by the end of September, where we can assess the staff thereafter. Security Questionaires will form part of the training schedule in the points above. This can be closed once thats achieved Update April 2024: Security Questionaire to be issued, due in April/May however will need time for return. Is now part of the schedule however and the re-evalution after a year. Update Aug 2024: Questionaire is created (shared in the evidence folder) and will be issued in the August of 24/25. This was the last item to complete this recommendation, HL to decide if that is enough to close this or do they need return information from the questionaire before they close the item. | **Please note date moved, question for HL about evidence for this, questonaire supplied in evidence folder
Cyber Security | Explore how guidance for staff on how to manage their digital footprints safely and reduce the risk of becoming a target for attackers, both in a professional and personal capacity, and particularly through use of social media platforms can be made more widely available to staff and Board members. | Heads of IT and HR | 3 | 2022-12-31 |  | Partially complete | 2024-11-01 | Social media guidance is already in effect, however follow up sessions and the impact of staff actions will form part of the training schedule details in the comments in the last few rows. Documentation is still under review, however a big improvement since this audit point has been with modifications to the azure platform to prevent 3rd party sign in without prior approval from the head of MIS, enforcing a culture of checking the app before logging in. Update in Nov - social media and comms policy needs to be looked at from the new marketing manager and security added to it. ETA is Feb 2024 Update April 2024: Suggest that the final part of this item is with the marketing and comms manager for completing and issuing the social media comms policy. Hope the ETA could be by the end of May Update August 2024: Social media policy is in draft and needs approved by SLT and Board in November. ETA for publication is Nov 2024 | **Please note date moved, awaiting board approval for policy
Cyber Security | The Incident Response Process, and supporting playbooks, should be tested by way of a scenario-based desktop exercise to ensure staff know how to respond during an incident, and to also highlight any problem areas in the planned response. | Heads of IT and HR and the Clerk to the Board | 2 | 2023-03-31 |  | In progress | 2024-09-01 | Incident response documents exist along with playbooks. Will need review and updated before December. Training for the senior leadership team is scheduled for some time in October. Training for the SLT needs to go on the agenda for the new year. ETA Feb 2024 Update April 2024: SLT availablity has been limited, the incident reponse document has been recently reviewed and training for the SLT will be by the end of May. Closure of this item due at that point Update August 2024: SLT will get training at the beginning of the year 24/25 and the presentation/scenario that we use can be shared as evidence of the incident response trianing | **Please note date moved
Health & Safety | We recommend that a programme of refresher training for staff should be developed to coincide with the launch of the revised Occupational Health and Safety Policy and associated procedures. Attendance at this refresher training should be mandatory for all members of staff and completion of the training should be monitored by HR to ensure full attendance. | Head of Facilities & HS, Head of HR | 3 | 2022-12-31 |  | Partially complete | 2024-09-24 | This will be done in association wih the Health and Safety team as per the the launch of the policy. HR will provide generic H&S training as part of the e-learning suite. Health & Safety Officer issued email in this regard on 21st August; sessions will roll out and expect to be completed by end of Nov 2023. (CF) This is ongoing once resourse is available (CF) Jan 24: e-learning course has been rolled out to all staff on "Health & Safety in Education (Colleges & Universities). 197 people have comleted the training, 132 are in progress and 6 people have not yet started the training. Aug 24 - Standard mandatory training has been completed and specific H&S training, Fire Wardens, First Aiders etc has also been carried out with a minimal number of refreshers on FA to be completed (CF)
Health & Safety | We recommend the reporting of an Annual Health and Safety Report be incorporated into the forward workplan for the Human Resources Committee to ensure that Board Members have the opportunity to consider and approve the annual report and the forward workplan for health and safety activity for the coming year. | Head of Facilities & HS | 3 | 2022-12-31 |  | Partially complete | 2024-11-24 | An annual report will be produced reporting on what has been completed during the year and set out the priorities and targets for the coming year. Staff absence has caused a delay in this piece of work progressing more fully but it will be carried out imminently for review at a future HR Committtee.(CF)
Risk Management | A session on risk management should be included as part of the programme of Board Member Strategy Days with the leadership team. This will allow greater understanding on how the risks link to the College’s strategic aims and objectives and the impact failure to manage these risks will have on future success. To support Board assurance, management should conduct an assurance mapping exercise on the internal and external reporting arrangements in place against the current risks on the risk register. This will allow for a central analysis of the arrangements in place and allow any gaps to be identified and appropriate supplementary reporting arrangements determined. Assurance mapping can be completed by adding additional columns to the existing risk register detailing the following sources of assurance established: • Internal - management reporting and quality assurance arrangements; and • External - internal audit, external audit, Education Scotland etc. Assurance reporting can then be brought into the forward planning for Board and committee agendas | Principalship | 3 | 2022-08-31 |  | Partially complete | Dec-24 | Internal audit providers Henderson Loggie presented a seminar on Strategic Risk Management at the Board training day in 2nd May 2023. The session incorporated separate workshops on setting the tone for risk management and risk assurance. Risk Policy and Procedures are to be updaed. August 2024: An assurance mapping exercise is yet to be undertaken at the Audit and Risk Committee. This is being targetted for circa 19th November 2024, when the College is hosting a Board Training Day with all existing and recent Board appointments to look specifically at Risk Appetite. In the meantime, the Governance Professional is bringing an update on Risk Strategy and Governance to the Audit & Risk Committee on 26th August 2024. .
2022/23
Staff Recruitment & Retention | It is recommended that the College define timeframes for completion of the ongoing review of its recruitment and selection policies to ensure that these are completed in a timely manner and are issued to the relevant staff for their understanding. | Head of HR | 2 | 2024-01-20 |  | In progress | 2024-11-01 | The College is currently refreshing dated policies and implementing policies where there are gaps. This year, the Human Resources Committee has agreed to a recruitment policy being part of the next suite of new policies being implemented.
Staff Recruitment & Retention | It is recommended that the College prepare procedural documents to formally document the administration processes to be followed when recruiting a new member of staff, to ensure that the process can be consistently performed by anyone in the event of staff absences / unexpected turnover. | Head of HR | 3 | 2024-05-20 |  | In progress | 2024-11-01 | The College is currently refreshing dated procedures and implementing procedures where there are gaps. This year, the Human Resources Committee has agreed to a recruitment procedure being part of the next suite of new procedures being implemented.
Staff Recruitment & Retention | It is recommended that the College set out a clear timeline for importing all relevant hard copy documentation to the new HR system iTrent, to ensure that this data transfer is completed in a timely manner and to avoid a protracted scenario where some information is held electronically and some information is still held in hardcopy files | Head of HR | 3 | 2024-05-20 |  | In progress | 2024-12-24 | Following the implementation of the new HR System, the College will propose the importing of hard copy documentation. This will allow the College time to understand the time and process necessary to undertake this task. The College will aim to have a project plan for the importation by 20th May 2024. August 24: the project plan for importation has been delayed due to delays in the HR System project. It is now envisaged to be created by 1st December 2024.
Staff Recruitment & Retention | It is recommended that the College implement ongoing engagement measures to capture levels of staff satisfaction to reduce the risk of employees leaving the employment of the College due to issues which could have been managed and resolved had they been identified earlier. | Head of HR | 3 | 2025-11-20 |  | In progress | 2025-11-01 | The College has historically measured engagement through various surveys. Whilst there have been regular surveys, they have followed the structure required by third party accreditations and have not provided the College with an engagement framework that is measured over time and across the employee journey. The College recognises this. It is included it in the HR & People Strategy. August 24: The College is currently implementing an employee engagement framework and an initial action plan. The framework was recently introduced to staff at the recent Staff Conference Day on 13th August 2024 and engagement will be measured over time.
Budgetary Control | The College should develop a formal budget setting timetable, setting out all key activities in the budget setting process from end to end, to ensure that all activities are completed timeously. The timetable may also assign tasks to responsible individuals, with target completion dates aligned with the Finance and Resources Committee meeting as appropriate. | VP - Finance, Resources & Sustainability | 3 | 2024-01-31 |  | In progress | Feb-25 | Finance team is currently preparing a timetable for the Budget setting process across Feb - May 2024, aligning with the Curriculum Plan. August 2024: A draft budget setting process has been prepared and shared with our internal auditors and will be further enhanced with procedure steps as the Finance Team work towards the completion of the Budget setting process for 25/26.
Budgetary Control | The College should consider developing enhanced real time financial information and dashboards, perhaps via Power BI, to allow Budget Holders to monitor actual income and expenditure against budget in real time. | VP - Finance, Resources & Sustainability | 3 | 2024-02-29 |  | In progress | Feb-25 | Finance currently working with the Head of IT to further develop Power Bi information to enhance reporting capability and results monitoring. August 2024: As was communicated to Internal Audit at the start of the month, work is ongoing and progress is being made to further build out Power BI capability within financial reporting. Budgets for 24/25 rely on reports and month end income accruals/deferrals will also be centred around Power BI reports.
Budgetary Control | The Finance team should document the month end process currently followed by Finance, including preparation of budgeting information to allow for prompt publication of income and expenditure by budget line for review and monitoring by Budget Holders. This should be adapted as the capabilities of BluQube are enhanced to include generation of reports immediately following the completion of the month end close process to provide timely information. | VP - Finance, Resources & Sustainability | 3 | 2024-03-31 |  | In progress | Mar-25 | The Finance Department are in the process of updating and formalising its operating and reporting calendar. August 2024: Work is still ongoing to devise a full process and process notes will be built out as the process is embedded. The FInance System is being enhanced with consultancy input in September 2024 and the College has purchased the reporting package to enable monthly reports to be run directly from the system with ease.
Budgetary Control | The College should develop a formal training programme for Budget Holders, which they are required to complete before they undertake their budget monitoring role. Detailed written procedures and guidance documents should also be developed (in parallel with the development of this tailored training for Budget Holders). This will provide a useful reference document for all Budget Holders, which they can consult, as required, following the training. | VP - Finance, Resources & Sustainability | 3 | 2024-05-31 |  | Not yet started | Mar-25 | August 2024: A formal training programme has yet to be put in place but allowing for 6 month period to embed the Bluqube reporting package and have it fully operational, the College would expect to roll out training to budget holders in conjunction with new reporting system capabilities.
Student Support Funds | The College should ensure that distribution lists identifying Bursary students in receipt of study materials are maintained for each purchase invoice charged to the Bursary fund. Based on the current approach, the College should ensure that the planned study costs for each course still reflect the specific items or materials needed for the course and the current price from suppliers. | Management Accountant | 3 | 2024-02-29 |  | In progress | 2024-09-01 | The College will continue to analyse all study costs monthly and reconcile back to Cost of Course forms, adjusting the Teqios system where required, and reconciling this to the general ledger. With regards to distribution lists we will endeavour to implement a process whereby the students receiving bursary items are either listed on the actual invoice or on the original purchase order or if this is not possible on an attached document.
Student Support Funds | Ensure that a check is made on the categorisation of ASN costs to ensure that they are correctly disclosed on the FES. | Management Accountant | 3 | 2024-02-29 |  | In progress | 2024-09-01 | An additional step will be added to the FES reconciliation process to ensure that there is a clear distinction made between actual travel expenses and travel related ASN costs before the FES is submitted. It is intended that this will be demonstrated and closed off during the audit that is scheduled to take place w/c 25th August 2024.
Student Activity (Credits) | Ensure that Credits claimed for students on part-time programmes are based upon the value of the units listed on the discrete course record, or notional Credits based on planned hours of activity divided by 40, and not based upon a default tariff. | Head of MIS | 3 | 2024-09-30 |  | In progress | Sep-24 | SLC will endeavour to ensure that the credit matching process between claim and the units attached to students are accurately done. In addition, a check for the credits not meeting 0.25 multiples will be put in place. Review of this during the quarter returns should be sufficient to close this recommendation, checked again in the final return next year.
Student Activity (Credits) | Ensure that the Credits claimed for flexible learning courses adequately reflects the level of activity undertaken in the year. | Head of MIS | 3 | 2024-09-30 |  | In progress | Sep-24 | SLC Spanning course must make sure that they only claim what they teach within the year. The 22/23 ESOL ICDL course was adjusted downwards as there wasn’t reasonable time to complete the work. However, good controls are already in place for Spanning / Cross Sessional courses via the power bi reporting and the management of course from one year to another. Feedback to the AP’s and CM’s is that they must maintain their course and not front load courses that fall into this format. Monitoring of this will be quarterly, however, final return will confirm that this recommendation can be closed.
Student Activity (Credits) | Ensure that the required date input into SITS is calculated in line with the SFC guidance. | Head of MIS | 3 | 2024-09-30 |  | In progress | Sep-24 | This was an issue between the course required date and the student required date in the system. More care will be taken in the next year to ensure that the required dates are accurate in the system and that the FES output takes the information from that field. It is expected to be correct but as the year goes on we will review as part of the quarterly return. Confirmation of this point will only close at the start of the next audit in Sept 2024.
2023/24
Publicity & Communications | Comprehensive social media guidelines should be developed in order to: • support staff who have direct access to College social media accounts; and • to guide staff in their use of personal social media in relation to information which pertains to their role within the College. | Marketing and Communications Manager | 3 | 2024-06-01 |  | In progress | Nov-24 | SLC agree that Social Media Guidelines are required to frame employees’ responsibilities. As noted by HL, this is captured within the Code of Conduct and is on the Marketing Action Plan. MArketing are working closely with MIS to devise appropriate guidelines and these will be brought to the next round of Committee/Board meetings in November/December 2024.
Publicity & Communications | Crisis communication training should be delivered for the Principalship and the Marketing and Communications Manager. | VIce Princioal - Learning, Teaching & Student Experience | 3 | 2024-07-31 |  | In progress | Mar-25 | The Principal and Vice-Principal for Learning, Teaching & the Student Experience are comfortable with the level of training they have received to date. The Vice Principal - Finance, Resources & Sustainability and the Marketing and Communications Manager will undertake Media/Crisis Training with Police Scotland on 25th March 2025.
Procurement & Creditors/Purchasing | It is recommended that consideration be given to amending the approvals of low value purchase orders in PECOS to Vice Principals and Associate Principals (rather than requiring sign off by the Principal), to reduce the risk of a bottleneck. | Vice Principal - FInance, Resources & Sustainability | 3 | 2024-06-30 |  | In progress | Nov-24 | The Vice Principal – Finance, Resources & Sustainability has included a revised proposal for PO authorisation / delegation within the finance regulation updates for FRC committee on 15th May 2024., The College Finance Team is progressing with plans to embed changes in PECOS to support the new structure now, aligning named individuals to the strucures mandated by the Finance Regs. It is expected that the mapping will be complete by the next round of committee meetings in November 2024.
Procurement & Creditors/Purchasing | It is recommended that the College formalise its process for recording changes to supplier’s standing information (including bank details and addresses) by implementing a standard form to document the independent checks undertaken to verify the changes, with a peer review / management review step implemented to ensure that there has been independent review of the changes made to supplier standing data prior to any payment being made to the relevant supplier following the application of the changes on the system. | Vice Principal - FInance, Resources & Sustainability | 3 | 2024-06-30 |  | In progress | Nov-24 | A draft form has been prepared by the Finance team. This new format now needs to be authorised by the line manager in the team and after this, the audit point can be closed off imminently and confirmed by the next ARC in November 2024.

## Rolling Review (Completed)
Audit Recommendations Monitor
2023-10-03
Report / Action | Recommendation | Action Owner | Grade | Original timescale | South Lanarkshire College management update as at April 2020 | Status at 18 August 2023 | Expected Completion Date | South Lanarkshire College management update as at 29 September 2023 | Date of Next Review
2019/20
Payroll and Expenses | The College should review and, if necessary, update the Expense Procedural Manual in line with its version control information. | Head of Finance | 1 | 2020-10-01 | The Finance Dept is in the process of reviewing all of its policies and procedures as part of a College-wide exercise. An update in the internal process for changing policies and procedures requires that any changes are run through an internal management cycle. The expenses procedures are not expected to change per se, but they will have to be formally reviewed as above via the SLT and CLT. | Complete | N/A | The College's Financial regulations were updated and were approved by the Finance and Resources Committee in April 2022. The controls in that document flowed into an updated Expense Procedure Manual which was presented to the SLT as per the new procedures for policy approvals in February 2023 before being presented to and approved by the Finance Committee. | 2024-04-01
2019/20
Strategic Planning | SLC should conduct a structured and documented analysis of stakeholders and key groups to record and assess the level of influence and interest each has with the SLC’s operations. | Depute Principal | 2 | To be confirmed – for the next round of Strategic Planning | The Board of Management is having a Strategic Planning session (August 2021) and will have one each year to ensure that the strategic focus of management is in sync with Board thinking. The College also published a Strategic Framework document for the period 2020 - 2025 after extensive consultation with stakeholders, both internal and external. | Complete | N/A | Stakeholder newsletter issued in May / June and College has had meetings with a range of stakeholders and Board members. The College has also been engaging with the South Lanarkshire Community Planning Partnership. The latter has resulted in a grant from the Shared Prosperity Fund.
2020/21
No recommendations outstanding
2021/22
Cyber Security | To effectively communicate the College’s risk management approach to management and Board members, so that they understand how cyber security risks should be managed and to help them make decisions about them, updates on the cyber threat landscape, events, actions, and plans surrounding cyber security within the College and the sector should be reported to the Management Team and to the Board regularly. Reporting should include a summary of the top-rated risks on the College cyber risk register (see R1) and details of mitigations already in place and those further required. | Head of IT and Clerk to the Board | 3 | 2022-12-31 |  | Complete | 2023-03-01 | This follows on from the risk register setup above. Once we're comfortable with the formal review of the documentation and it has been agreed by the auditors, this can be shared with the risk committee. In addition, the Head of IT provides an update report to SLT at least once a term on cyber security. The Board now consider a minimum of two reports a year on cyber security.Cyber security posture/incidents are now reported to the board. The mitigations and the list of the threats were presented to the board at the last board strategy day. | 2024-09-01
Cyber Security | Establish mandatory requirements within procurement procedures for relevant suppliers to provide evidence of current cyber security certifications. Also ensure that relevant suppliers provide copies of recertifications when these are due. | Head of Finance | 3 | 2022-10-31 |  | Complete | N/A | This is complete. There is a separate form supplied by APUC to successful tenderers and the information is retained on their Supplier Chain Management (SCM) system. | 2024-09-01
Cyber Security | Establish mandatory requirements within procurement procedures for relevant suppliers to provide evidence of current cyber security certifications. Also ensure that relevant suppliers provide copies of recertifications when these are due. | Head of Finance | 3 | 2022-10-31 |  | Complete | N/A | This is complete. There is a separate form supplied by APUC to successful tenderers and the information is retained on their Supplier Chain Management (SCM) system.
Health & Safety | We recommend that a timetable for Health and Safety Policy / Procedure Approval should be developed to ensure the timely update of the Occupational Health and Safety Policy (and related policies, procedures and guidance) and a timeline for consideration by the Health and Safety Committee and ultimately formal approval by the Board. This timetable should include an action to develop a Communications plan which will ensure a planned launch and roll out of the new policy framework and procedures so that all staff and students are aware of the new Policy and procedures and know where to find the information which sets out their respective responsibilities. | Depute Principal/ Heads of Health & Safety and Estates | 3 | 2022-11-30 |  | Complete | N/A | The Health and Safety Policy was approved by the Board of Management in November 2022. The policy is now live and all staff are required to read and accept the policy upon sign in. The Health and Safety Coordinator is putting together a series of briefing sessions to advise staff of the main changes. | 2024-09-01
Health & Safety | The wording around the reporting of near misses in the new Policy should include specific wording which clearly defines the types of near misses which should be reported and those which do not need to be reported. | Depute Principal / Heads of Health & Safety and Estates | 3 | 2022-10-31 |  | Complete | N/A | This has been added to the First Aid Policy and training to support will follow. | 2024-09-01
Health & Safety | We recommend that a timetable for Health and Safety Policy / Procedure Approval should be developed to ensure the timely update of the Occupational Health and Safety Policy (and related policies, procedures and guidance) and a timeline for consideration by the Health and Safety Committee and ultimately formal approval by the Board. This timetable should include an action to develop a Communications plan which will ensure a planned launch and roll out of the new policy framework and procedures so that all staff and students are aware of the new Policy and procedures and know where to find the information which sets out their respective responsibilities. | Depute Principal/ Heads of Health & Safety and Estates | 3 | 2022-11-30 |  | Complete | N/A | The Health and Safety Policy was approved by the Board of Management in November 2022. The policy is now live and all staff are required to read and accept the policy upon sign in. The Health and Safety Coordinator is putting together a series of briefing sessions to advise staff of the main changes.
Health & Safety | The wording around the reporting of near misses in the new Policy should include specific wording which clearly defines the types of near misses which should be reported and those which do not need to be reported. | Depute Principal / Heads of Health & Safety and Estates | 3 | 2022-10-31 |  | Complete | N/A | This has been added to the First Aid Policy and training to support will follow.
Risk Management | Operational leads should be reminded of their roles and responsibilities in relation to risk management and use of the AIR Logs for the documentation of risks identified. On reinstating the RMG, its remit should be updated and arrangements for the reporting of Operational Risk Registers to the group clearly defined. The future RMG standing agenda should include the review of emerging risks arising from projects and capital works. | Depute Principal | 3 | 2022-10-31 |  | Complete | N/A | Review of the Strategic Risk Register is now a standing item on the Risk Management Group agenda with the Register being reviewed prior to it being considered by the Senior Leadership Team. SLT business now includes review of the College's AIRlog and consideration of major items of spend. | 2024-05-01
Risk Management | The College’s risk appetite for differing risk categories requires to be set by the Board so that resources (people, time and money) can be aligned to mitigating actions for risks that are approaching or exceed the College’s agreed risk appetite levels. Risk appetite should also be reviewed annually or when there are significant changes in Board membership. Risk appetite for risk categories should be documented on the Strategic Risk Register to allow comparison against residual risk levels. Treatment of risks should also be considered as part of this exercise. Risk appetite and risk treatment arrangements should be documented in the Risk Management Policy and Procedures to ensure organisational knowledge and transparency on arrangements. | Depute Principal | 3 | 2022-10-31 |  | Complete | N/A | Risk appetite was considered by the Audit and Risk Committee in May 2023 and the Board of Management in June 2023. Risk appetite is an annual exercise for the Board to consider. | 2024-05-01
Risk Management | All risks should be linked to strategic objectives to ensure there is a golden thread from the College’s strategy and performance requirements to the risks identified at a strategic and operational level. All risks and (associated mitigating actions) should have a single delegated owner to allow effective assessment of the appropriateness of the resource deployed to maintain mitigating controls and progress mitigating actions required to manage individual risks. | Depute Principal | 3 | 2022-09-30 |  | Complete | N/A | All risks now linked to strategic objectives and all have a single dedicated owner. | 2024-05-01
2023/24
Staff Recruitment & Retention | When onboarding new employees, it is recommended that copies of all original qualifications and right to work documentation held on file are signed as being reviewed and confirmed as an original document by the HR officer who was presented with the document for copying | Head of HR | 3 | 2024-12-20 |  | Completed | 2023-09-01 | The College agrees that by signing the copies as “original sighted”, this would be further evidence of this process being implemented.
Cyber Security | Review and reconfigure the cyber training compliance reporting parameters to ensure that data reported consists of current users only. The data reported can then be used more meaningfully by Organisational Development, departmental line managers, and the Head of Information Systems and Services to monitor staff compliance rates. | Heads of IT and HR | 3 | 2023-06-30 |  | Completed | Mar-24 | The effectiveness of the training and the training materials have been sourced as part of the previous item. The stats that support this should follow on from the training communicated to staff. Update April 2024: As above the program of works will be monitored throughout the next two years, including phishing campiagns. The data is collected at departmental level in the TES develop software, as will the trianing program put together by the IT team. We also now have org structures in the M365 tenancy allowing us to understand patterns of behavour within departments. We consider this closed. | As above, TES develop stats are currently: 270 staff have completed so far 57 still to complete (82.6% of staff completed)
Cyber Security | A programme of information security training should be developed for students to mitigate information security risks covering: • the organisation’s IT security policies and procedures. • cyber security risks and strategies for defence, covering internet safety, mobile and home working, phishing, and prevention against malware. • regular updates and training on the security risks to the College. • monitoring the effectiveness of security training through incident monitoring and mock scenario testing; and • promoting an incident reporting culture. | Heads of IT and Student Services | 3 | 2023-02-28 |  | Completed | 2024-03-24 | This program is assoicated with the comments mentioned in the last two rows. This includes students and staff in the schedule The schedule was completed and shared before the end of Feb; the implementation is currently taking place at the start of the new term. Stats now available regarding the risky users and the implementation of the Microsoft Security tracking. Further work planned for the incident reponse and business continuity in the new year which should close this action Update April 2024: we now have a plan as part of the staff training above. Simple but effective campaigns have been put together by the IT team and the plan is available to be shared. Monitoring of effectiveness can be done via the M365 security dashboard Update August 2024: We have applied updates and changes to the M365 following a Jisc review, cyber risks are covered by an earlier point the incident response functions are switched on in M365 and are also addressed in a later item | M365 review document (redacted) and provided the retention policy as well. Screenshot of the risky users and 3rd party 365 settings that have now been applied. The review document says we need to do it, the screenshots proved we have done it.
Cyber Security | It is recommended that an audit of cloud and third-party systems in use across the College estate, which are not directly linked to College Active Directory or Office365 accounts, is undertaken to identify instances of staff using College logins and email accounts and put in place procedural guidance for line managers to revoke user access to such accounts, and for staff on good password management. Development of a digital asset register which combines the details of College hardware and software assets, as well as third party services operated by staff would provide clearer visibility of the College cyber and data risk profile. Any identified risks should then be included on the cyber risk register | Heads of IT and HR | 3 | 2023-01-31 |  | Completed | 2024-04-01 | Office 365 has now been fully implemented for 3rd party blocking of college accounts. Only approved apps can be used. Updates to HR will complete as part of the new HR system which will be completed in October, that will resolve the leavers and role change requirement for this point Update in Nov and Jan, awaiting the completion of the HR system and processes Update April 2024: Cyber risk register is now complete, the 3rd party access is now controlled, recent M365 reviews from JISC support our approach to the logins, HR now have good communication on starters and leavers, security review are in place for clear downs of old accounts, plus retention document has been issued in the last year which the IT team now adhere to. Item should be completed Update August 2024: Same as an item above, M365 review from JISC is provided to HL and we have in place the 3rd party and risky users parameters on office 365 | Screenshots and the summary document from JISC
Health & Safety | An exercise should be completed to update the master spreadsheet to demonstrate the number of issues identified and to record the remedial action taken. Once the master spreadsheet has been updated, the location of the master document on the server should be communicated to managers so that they can review and provide updates on any remedial action taken. | Head of Facilities & HS | 3 | 2022-12-31 |  | Partially complete | 2024-05-31 | The master log is being updated and any outstanding items pursued to provide an update. This will be shared with all relevant managers. Master H&S Housekeeping is maintained by facilities and required actions are rolled out to managers in the relevant departments. Due to resourse issues this is behind schedule. We are making best endevoures to fill this gap by increasing H&S role from 3 to 5 days as previous member of staff was not replaced. (CF) Housekeeping log is being updated at this point and I expect completion to be May 2024 (CF) This has been completed and will contrinue to be completed alongside the housekeeping inspections thought the method of closure is improved by being checked by H&S Advisor(CF Aug 2024) | Housekeeping log available
Cyber Security | Formally document the College's specific cyber security risks and vulnerabilities, along with controls and mitigations, within an IT or cyber risk register. Format should be in line with the College's strategic risk register. | Heads of IT and Finance | 3 | 2022-12-31 |  | Completed | 2024-04-24 | The cyber risks detailed in the NCSC 10 things have been collated into a framework that we can demonstrate to the committee and the auditors. New framework template is currently being discussed with the HEFESTIS cyber security shared service and progress has been made to ensure all risks have been mitgated or progress has been made towards the mitigation Update Nov: Progress as we have been awaiting on this from scottish government, update due Dec 2023 with the old framework if the new framework still hasn't been issued Update Jan 24 - Scottish Government now released document this will be finished by April with evidence for all the CRF answers. Update April 2024: Risk regsiter now complete the new CRF from scottish government we are now part of the pilot for roll out, but have been using the current CRF to monitor the risks in the department. Action should now be completed | CRF and Risk Register supplied
Cyber Security | Ensure that a formal programme of refresher training is established for staff users with a risk-based approach adopted in identifying the frequency of refresher training requirements | Heads of IT and HR | 3 | 2023-06-30 |  | Completed | 2024-04-01 | A program that has been written up by the Head of IS and the HEFESTIS shared service has now been implemented. This involves the various training that staff potentially could be lacking and align to the risk stated in the register mentioned above. Cyber security has been purchased as part of a suite of e-learning materials and training has been rolled out.The training has been rolled out at the beginning of term and stats from this e-module will support the interaction with the staff on this basis. Update Nov: The training has been issued to staff and we are still waiting for the analysis of the results. Further training for the year is planned and the schedule of this should be available in the next month (Dec 23) Update Jan 24: 3 employees have not yet started the training, 231 have completed the training and 99 people are in progress with the training. Update April: Following the feedback from the HR team above with the stats of cyber security training, the IT team have brought together a 2 year program of campaigns covering the major risks with a view to refresh the training for staff and students. We believe this to be closed | Cyber security training schedule supplied
Student Activity (Credits) | Ensure that in-year data integrity checks of the FES 1 and FES 2 data include a review of Modes of Attendance, and other key data such as Credits claimed, to identify conflicts and that data is amended as required. | Head of MIS | 3 | 2024-03-31 |  | Completed | 2024-06-01 | This requires the data checks during the quarterly returns to be more thorough. Introduction of a new student record system where the data entry will be better validated will help but that won’t be complete for the next credit audit in 2024. Demonstration of the checking should be shown to the Head of MIS by the second Quarter (February) and a review of this point against that return can confirm that the staff are monitoring the information well. Yes Chris Sumner 31 March 2024 Update April 2024: Currently the FES Q2 return was checked and appeared to be complete. Q3 is in June and should confirm that modes of attendance are being properly recorded as alterations were require to full time courses which became "short full time". Partially complete at this stage until we can provide evidence of the check. Update August: Q3 submissions was successful, we use the power bi reporting screenshot can be used as evidence when demostrating that we are managing our data integrity | Screenshot of the power bi report
Staff Recruitment & Retention | It is recommended that in future when uploading documentation to the new HR system, that the College should take steps to ensure that all information is accurate prior to upload to the new HR system, and any amendments to the information held on file should be checked with the relevant stakeholder(s) where any issues are identified | Head of HR | 3 | 2024-05-20 |  | Completed | 2024-05-01 | The College accepts that an administrative error by a new employee had been missed. All other documentation in the file would confirm that this was a mistake. Additional checks will take place for future documentation checks. The new HR System will support this.