## SLC Summary
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 2025-04-24 | [5 empty] | RSRMG
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 2025-04-24 | [5 empty] | May 2025
|  |  | Next date of review (Expected not actual) |  |  |  | 2025-07-31
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner | Risk Appetite Category | Risk Appetite | Nov previous risk score | Nov post-mit score | Edit Check! | Edit Check!
Data / Info Management
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of MIS | Information | Cautious | 6 | 3 | 0 | 0
Finance
1 | That the College cannot maintain financial stability | 3 | 5 | 4 | 20 | 20 | 0 | 5 | 4 | 20 | 20 | 0 | VP for Finance, Estates and Sustainability | Financial | Cautious | 20 | 20 | 0 | 0
2 | That there is a failure of financial controls | 3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | VP for Finance, Estates and Sustainability | Financial | Cautious | 15 | 10 | 0 | 0
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,2,3 | 5 | 3 | 15 | 15 | 0 | 5 | 1 | 5 | 5 | 0 | VP for Learning & Teaching | Financial | Cautious | 15 | 5 | 0 | 0
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 3 | 12 | 12 | 0 | 4 | 3 | 12 | 8 | 4 | VP for Finance, Estates and Sustainability | Financial | Cautious | 12 | 12 | 0 | -4
Governance
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | Governance Professional | Governance | Minimal | 8 | 4 | 0 | 0
Health and Saftey
6 | That there is a failure to meet statutory and legislative health and safety. | 2 | 4 | 3 | 12 | 12 | 0 | 4 | 2 | 8 | 8 | 0 | Head of Estates | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
Legal/Compliance
4 | That there is a breach of legislation and associated regulations (incl. GDPR, HR, Quality, finance) | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of MIS | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 3 | 0 | Executive Team | Legal/Compliance | Cautious | 9 | 3 | 0 | 0
15 | That the College is not on track to meet the Scottish Government net zero sustainability priorities. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | VP for Finance, Estates and Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
Operations
9 | That there is a failure to achieve high standards of learning and teaching and assessment. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | VP for Learning & Teaching | Operations | Open | #N/A | #N/A | #N/A | #N/A
12 | That the College cannot provide a robust learner experience supporting them onto positive destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 3 | 12 | 8 | 4 | VP for Learning & Teaching | Operations | Open | #N/A | #N/A | #N/A | #N/A
People | [18 empty] | 0
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | Head of HR | People | Eager | 8 | 4 | 0 | 0
Property
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 3 | 2 | 6 | 6 | 0 | 3 | 2 | 6 | 3 | 3 | Head of MIS | Property | Minimal | 6 | 6 | 0 | -3
Strategy
14 | That there is a reputational risk to the College. | 3 | 4 | 4 | 16 | 16 | 0 | 4 | 3 | 12 | 12 | 0 | Principal | Strategy | Open | 16 | 12 | 0 | 0
College Strategic Objectives: | [7 empty] | Risk Key | Low | 1-3
1 | Student Experience | [7 empty] | Medium | 4-9
2 | Culture and People Development | [7 empty] | High | 10-19
3 | Growth and Innovation | [7 empty] | Very High | 20-25
4 | Sustainability