## General
Audit Recommendations Monitor
2025-04-29
Report / Action | Recommendation | Action Owner | Grade | Original timescale | Status at 29 April 2025 | Expected Completion Date | South Lanarkshire College management update as at 29 April 2025 | Evidence Supplied
2021/22
Cyber Security | The Incident Response Process, and supporting playbooks, should be tested by way of a scenario-based desktop exercise to ensure staff know how to respond during an incident, and to also highlight any problem areas in the planned response. | Heads of IT and HR and the Clerk to the Board | 2 | 2023-03-31 | In progress | 2025-06-25 | Incident response documents exist along with playbooks. Will need review and updated before December. Training for the senior leadership team is scheduled for some time in October. Training for the SLT needs to go on the agenda for the new year. ETA Feb 2024 Update April 2024: SLT availablity has been limited, the incident reponse document has been recently reviewed and training for the SLT will be by the end of May. Closure of this item due at that point Update August 2024: SLT will get training at the beginning of the year 24/25 and the presentation/scenario that we use can be shared as evidence of the incident response trianing Update November 2024: SLT training still needs to be organised, now aiming for the staff development day in December with intention to make this a regular refresher for the group. This is in alignment with work going on with the BCP Update January 2025: SLT training to be arranged; targetting March 2025 Update April 2025: Due tot he changes in SLT staff following the restructure, it makes sense to move this back to later in the year or next session. I'll set the deadline for this for June 2025 but it could be Sept 2025 before it's completed. | **Please note date moved
Health & Safety | We recommend the reporting of an Annual Health and Safety Report be incorporated into the forward workplan for the Human Resources Committee to ensure that Board Members have the opportunity to consider and approve the annual report and the forward workplan for health and safety activity for the coming year. | Head of Facilities & HS | 3 | 2022-12-31 | Partially complete | 2025-05-30 | An annual report will be produced reporting on what has been completed during the year and set out the priorities and targets for the coming year. Staff absence has caused a delay in this piece of work progressing more fully but it will be carried out imminently for review at a future HR Committtee.(CF) Apr '25 - Date moved out to allow for completion of report CF
2022/23
Staff Recruitment & Retention | It is recommended that the College define timeframes for completion of the ongoing review of its recruitment and selection policies to ensure that these are completed in a timely manner and are issued to the relevant staff for their understanding. | Head of HR | 2 | 2024-01-20 | In progress | 2025-08-01 | The College is currently refreshing dated policies and implementing policies where there are gaps. This year, the Human Resources Committee has agreed to a recruitment policy being part of the next suite of new policies being implemented. | **Please note date moved
Staff Recruitment & Retention | It is recommended that the College prepare procedural documents to formally document the administration processes to be followed when recruiting a new member of staff, to ensure that the process can be consistently performed by anyone in the event of staff absences / unexpected turnover. | Head of HR | 3 | 2024-05-20 | In progress | 2025-08-01 | The College is currently refreshing dated procedures and implementing procedures where there are gaps. This year, the Human Resources Committee has agreed to a recruitment procedure being part of the next suite of new procedures being implemented. | **Please note date moved
Staff Recruitment & Retention | It is recommended that the College set out a clear timeline for importing all relevant hard copy documentation to the new HR system iTrent, to ensure that this data transfer is completed in a timely manner and to avoid a protracted scenario where some information is held electronically and some information is still held in hardcopy files | Head of HR | 3 | 2024-05-20 | In progress | 2025-05-01 | Following the implementation of the new HR System, the College will propose the importing of hard copy documentation. This will allow the College time to understand the time and process necessary to undertake this task. The College will aim to have a project plan for the importation by 20th May 2024. Apr 25: the project plan for importation has been delayed due to delays in the HR System project. It is now envisaged to be created by 1st May 2025.
Budgetary Control | The College should develop a formal budget setting timetable, setting out all key activities in the budget setting process from end to end, to ensure that all activities are completed timeously. The timetable may also assign tasks to responsible individuals, with target completion dates aligned with the Finance and Resources Committee meeting as appropriate. | VP - Finance, Resources & Sustainability | 3 | 2024-01-31 | In progress | Aug-25 | Finance team is currently preparing a timetable for the Budget setting process across Feb - May 2024, aligning with the Curriculum Plan. Apr 25; As advised previously, a draft budget setting process has been prepared and shared with our internal auditors and will be further enhanced with procedure steps as the Finance Team work towards the completion of the Budget setting process for 25/26. With a new Head of Finance only recently in post, the College will conclude the Budget setting process in May and bring an update to the Committee in Aug 2025 | **Please note date moved
Budgetary Control | The College should consider developing enhanced real time financial information and dashboards, perhaps via Power BI, to allow Budget Holders to monitor actual income and expenditure against budget in real time. | VP - Finance, Resources & Sustainability | 3 | 2024-02-29 | In progress | Jul-25 | Finance currently working with the Head of IT to further develop Power Bi information to enhance reporting capability and results monitoring. Apr 25: As was communicated to Internal Audit at the start of the month, work is ongoing and progress is being made to further build out Power BI capability within financial reporting. Budgets for 24/25 rely on reports and month end income accruals/deferrals will also be centred around Power BI reports. | **Please note date moved
Budgetary Control | The Finance team should document the month end process currently followed by Finance, including preparation of budgeting information to allow for prompt publication of income and expenditure by budget line for review and monitoring by Budget Holders. This should be adapted as the capabilities of BluQube are enhanced to include generation of reports immediately following the completion of the month end close process to provide timely information. | VP - Finance, Resources & Sustainability | 3 | 2024-03-31 | In progress | Jul-25 | The Finance Department are in the process of updating and formalising its operating and reporting calendar. Apr 25; Work is still ongoing to devise a full process and process notes will be built out as the process is embedded. The FInance System was enhanced with consultancy input in September 2024 and the College has purchased the reporting package to enable monthly reports to be run directly from the system with ease. With the new Head of Finance in post the College anticipates more progress on this point over the coming months. | **Please note date moved
Budgetary Control | The College should develop a formal training programme for Budget Holders, which they are required to complete before they undertake their budget monitoring role. Detailed written procedures and guidance documents should also be developed (in parallel with the development of this tailored training for Budget Holders). This will provide a useful reference document for all Budget Holders, which they can consult, as required, following the training. | VP - Finance, Resources & Sustainability | 3 | 2024-05-31 | Not yet started | Jul-25 | Apr 25: A formal training programme has yet to be put in place but allowing for 6 month period to embed the Bluqube reporting package and have it fully operational, the College would expect to roll out training to budget holders in conjunction with new reporting system capabilities in 25/26. | **Please note date moved
Student Support Funds | The College should ensure that distribution lists identifying Bursary students in receipt of study materials are maintained for each purchase invoice charged to the Bursary fund. Based on the current approach, the College should ensure that the planned study costs for each course still reflect the specific items or materials needed for the course and the current price from suppliers. | Management Accountant | 3 | 2024-02-29 | In progress | Jul-25 | The College will continue to analyse all study costs monthly and reconcile them back to Cost of Course forms, adjusting the Teqios system where required, and reconciling this to the general ledger. With regards to distribution lists, the College has implemented a document during the monthly reconciliation process that lists all bursary students and their course code/spend available however this did not tie in to actual spend. The College therefore accepts the action required now to attach actual spend to this document and will work with the curriculum managers to see if a better record of study cost spend can be kept at class level. The College commits to resolving this over the summer with a view to it being evidenced and confirmed in the next FES return audit in Sep 25.
Student Support Funds | Ensure that a check is made on the categorisation of ASN costs to ensure that they are correctly disclosed on the FES return. | Management Accountant | 3 | 2024-02-29 | In progress | Jul-25 | The monthly categorisation check of FES categories will include a check of ASN costs to ensure that they are being disclosed correctly going forward. This is monitored from Aug - Jan then implemented from Feb - Jun once full quote of students are included on the FES return.
2023/24
Publicity & Communications | Crisis communication training should be delivered for the Principalship and the Marketing and Communications Manager. | VIce Princioal - Learning, Teaching & Student Experience | 3 | 2024-07-31 | In progress | Dec-25 | The Principal and Vice-Principal for Learning, Teaching & the Student Experience are comfortable with the level of training they have received to date. The Vice Principal - Finance, Resources & Sustainability and the Marketing and Communications Manager will undertake Media/Crisis Training with Police Scotland. Due to illness, the Vice Principal was unable to attend the event on 25th March 2025. Another session will need to be booked in its place.
Procurement & Creditors/Purchasing | It is recommended that consideration be given to amending the approvals of low value purchase orders in PECOS to Vice Principals and Associate Principals (rather than requiring sign off by the Principal), to reduce the risk of a bottleneck. | Vice Principal - FInance, Resources & Sustainability | 3 | 2024-06-30 | In progress | Sep-25 | The College Finance Team is progressing with plans to embed changes in PECOS to support the new structure now, aligning named individuals to the strucures mandated by the Finance Regs. However,given the ongoing College restructure and work that will be required to change the system parameters for new authorisations, this task has been delayed until a new College structure has been finalised to avoid unnecessary rework.
Student Activity (Credits) | Allocation of Credits to Courses R1 For all College devised units, the College should ensure that adequate supporting evidence is available for planned learning hours to verify the Credits claim. | Head of MIS (Chris Sumner) | 3 | Sep-25 | In progress | Sep-25 | College Units or “Non-SQA” units are a frequent issue. While I agree with the recommendation to get better at reporting the evidence, the college uses far fewer non-SQA units in their courses than previous years. That said, the timetabling and attendance for these modules needs improved using our current timetabling system. We will monitor this more closely with he timetabled hours vs actual hours power reporting as this was invaluable in the audit. At curriculum planning process, the CM’s will be challenged for using the non-SQA units, preventing unnecessary use of units in the courses. Record of work evidence is a lot clearer this year and can be used as supportive evidence for these modules.
Student Activity (Credits) | Required Dates and Attendance R2 Ensure that the required dates for programmes and students recorded on the FES1 and FES2, respectively, are calculated in line with the Credits guidance. | Head of MIS (Chris Sumner) | 3 | Sep-25 | In progress | Sep-25 | Required date issues was not an issue at course level but it was at student level if the student finished early. The power bi report we use for checking the required date has been modified so we can see the student required date might be incorrect and reviewed at each FES quarter returns. April 2025 Update: The report was updated and being reviewed by the staff. However, there is a question around the validity of moving a required date that we need to speak to the auditors about as it changes the way SFC view the required date. (CS to follow up with HL)
Student Support Funds | The College should ensure that expenditure is correctly categorised on the study costs spreadsheet to allow a more accurate comparison of planned and actual expenditure. | Management Accountant | 3 | Dec 24 | In progress | Jul-25 | The cost of course forms will be updated to show a more realistic split of bursary spend for each department, departments that have ‘other’ as a category of spend with no history of any actual spend within this category will have this amount spread over the other categories based on likely spend. Invoices that have a number of different categories of bursary spend will be allocated accordingly. This will be monitored from Aug - May and then implemented in June 25 once all spend is complete.
Student Support Funds | The College should review student Award Assessment categorisation on the FES and ensure that any apparent misstatements are fully investigated and resolved | Management Accountant | 3 | Dec 24 | In progress | Jul-25 | A monthly check of FES categories will be implemented to ensure any miscategorised students will have their details corrected by the student support team before any over/under payment takes place.
Businss Peocess Review Space Management/Room Utilisation | The College's Estate Strategy needs to be updated to reflect the current space requirements of the curriculum, staff, and students. | Head of Estates | N/A | 2024-11-30 | In progress | Jul-25 | The existing Estates Strategy is very outdated but an update has started and will be progressed in the coming months. Apr '25 - Date extended out to allow time to carry out CF | **Please note date moved
Businss Peocess Review Space Management/Room Utilisation | A centralised room booking system is required that is visible by the whole College. | Head of MIS/Head of Estates | N/A | 2025-08-31 | Not yet started | Dec-25 | The College agrees that there needs to be timetabling protocols and a room booking system that is visible and can be used by the whole College. This then allows for room utilisation data to be monitored. Apr '25 - New access control system and future tech to assist in enabling this. Date extended due to delay in tendering process CF | **Please note date moved
Businss Peocess Review Space Management/Room Utilisation | Space management objectives and room utilisation targets need to be clearly defined in policies and procedures, accompanied by a structured space utilisation monitoring process. | Head of Curriculum/Head of Estates/Head of MIS and Vixe Principal - Finance | N/A | 2025-12-23 | Not yet started | Dec-25 | Management agrees that policies and procedures (timetabling protocols and room booking) should be developed for cross college use. This is to be led by the curriculum area to enable support function departments to have systems in place. Apr '25 - Once procedures are in place, room utilisation can also use future access control technology for streamlined process CF | **Please note date moved
2024/25
Payroll amd Pensions Management | Review the capability within its Payroll team to prepare and submit the SPF member data for College employees in a timely and accurate manner. The College should consider strengthening the review and approval controls in place in relation to the data being submitted to the pension scheme administrators to minimise the risk of errors and subsequent inefficiencies in resolving SPFO’s and employees’ queries. The College should ensure that it is actively monitoring and enforcing the submission of accurate member data to ensure that the scenario where member data is out of date by several months does not reoccur. | Head of HR | N/A | 2025-05-31 | In Progress | May-25 | Completed except for the iConnect automation which is expected to be concluded by May 2025.
Payroll amd Pensions Management | The College should ensure that multiple employees, across both Payroll and HR departments, have access to e-mail inboxes where queries can be received from pension scheme members in relation to the College’s management of their pension data. This is especially important due to the high risk of errors and misalignment between data held by the College and the pension scheme administrators, as demonstrated throughout our review. | Head of HR | N/A | 2025-08-31 | In progress | 2025-08-01 | Completed except for the new Helpdesk System, which is expected to be concluded by end August 2025.
Payroll amd Pensions Management | The College should conduct a post-implementation review to provide confirmation that the new Payroll / HR system – iTrent – is configured in a way that provides adequate functionality for the management of employee pension data and allows the accurate, timely and efficient submission of required information to the pension scheme administrators. | Head of HR | N/A | 2025-05-31 | In progress | May-25 | This is in prigress
Payroll amd Pensions Management | The College should ensure that the new Payroll / HR system – iTrent – is configured in a way that offers adequate functionalities for managing employee pension data and assisting in accurately and efficiently submitting it to the pension scheme administrators. | Head of HR | N/A | 2025-05-31 | In progress | 2025-05-01 | This is in progress
Payroll amd Pensions Management | Pension scheme members’ leaving status should be communicated to the relevant pension agency promptly, accurately, and in line with their requirements. The College should review its controls around managing employee data on its payroll system and ensure that any staff members are removed from it on their actual leaving date. It should be made impossible to pay staff members who have left the College through regular payroll payment runs. Monitoring controls should be introduced (potentially independent to the Payroll team) over the payroll payment runs to ensure that no ex-employees are included in payroll payment runs past the month in which they have left the organisation. | Head of HR | N/A | 2025-04-30 | In progress | 2025-06-01 | Complete, with the exception of the reports being used as monitoring controls, which will commence in April 2025 and likely be in place for Jun 2025.
Payroll amd Pensions Management | The College should ensure that adequate internal controls are in place to prevent and detect illegitimate payroll transactions, ex-employees being included within payroll processing, and errors. Risk-averse monitoring, review, and approval controls should be implemented (or strengthened) to ensure sufficient segregation of duties in processing the payroll. The capabilities of the new iTrent HR & payroll system should be leveraged to establish appropriate user access rights and embed approval controls within the process. | Head of HR | N/A | 2025-04-30 | In progress | 2025-06-01 | Completed, with further reporting and monitoring commencing in April 2025, following the parallel runs.
Payroll amd Pensions Management | The College should consider undertaking a detailed exercise to determine how the historical overpayments to employees and pension schemes, as well as underpayments to HMRC, should be addressed and communicated to staff and other relevant stakeholders, including HMRC. The College should consider whether it has a complete view of instances where the ‘salary advance’ or other illegitimate adjustments were utilised and should take steps to determine whether these adjustments to HMRC payments are in any way connected to the fines levied by HMRC against the College in recent years | Head of HR | N/A | 2025-07-31 | In progress | 2025-07-01 | This is in progress